## Sheet1
CS 6400 Group Project |  |  | Revised: | 2019-07-15
Phase 3 Action Plan
Team 29
Members: Joseph Henn, Andrew Nagy, Ashkan Yousefi, Lei Fan
Item # | Action Item | Details | Member(s) | Est. Completion (EDT)
0 | Choose Tech Stack | Settled on WAMP | All | Done
1 | Demo Time & Presenter(s) | Choose demo time and who will present/backup. | JH | Done
2 | Design UI (Look & Feel) | Using online designer or by hand. No hard coding.
3 | Search Page | For both public & registered users. | AN | Done
4 | Search Results Page | For both public & registered users. | AN | Done
5 | Vehicle Detail Page | For both public & registered users. | AN | Done
6 | Add Customer | According to permission level. | AN | Done
7 | Sell Vehicle | According to permission level. | AN | Done
8 | Add Repair | According to permission level. | AN | Done
9 | Add Recall | According to permission level. | AN | Done
10 | Add Vehicle | According to permission level. | AN | Done
11 | View Reports | According to permission level. | AN | Done
12 | Seller History | Using project spec. |  | 2019-07-08
13 | Average Time in Inventory | Using project spec. |  | 2019-07-08
14 | Price per Condition | Using project spec. |  | 2019-07-08
15 | Repair Statistics | Using project spec. |  | 2019-07-08
16 | Monthly Sales | Using project spec. |  | 2019-07-08
17 | Inventory Age | Using project spec. |  | 2019-07-08
18 | Review and Approve UI Design | All team members sign off on design. | All | Done
19 | Setup Initial Files | Add WAMP directory to GitHub and ensure all can access. | JH | Done
20 | Implement MySQL Database | Using SQL schema from Phase 2. | JH | Done
21 | Implement Item 3 in PHP | Using approved UI design. See item number above. | JH | Done
22 | Implement Item 4 in PHP | Using approved UI design. See item number above. | JH | Done
23 | Implement Item 5 in PHP | Using approved UI design. See item number above. | JH | Done
24 | Implement Item 6 in PHP | Using approved UI design. See item number above. | JH | Done
25 | Implement Item 7 in PHP | Using approved UI design. See item number above. |  | 2019-07-12
26 | Implement Item 8 in PHP | Using approved UI design. See item number above. |  | 2019-07-12
27 | Implement Item 9 in PHP | Using approved UI design. See item number above. |  | 2019-07-12
28 | Implement Item 10 in PHP | Using approved UI design. See item number above. | JH | Done
29 | Implement Item 12 in PHP | Using approved UI design. See item number above. |  | 2019-07-14
30 | Implement Item 13 in PHP | Using approved UI design. See item number above. |  | 2019-07-14
31 | Implement Item 14 in PHP | Using approved UI design. See item number above. |  | 2019-07-14
32 | Implement Item 15 in PHP | Using approved UI design. See item number above. |  | 2019-07-15
33 | Implement Item 16 in PHP | Using approved UI design. See item number above. |  | 2019-07-15
34 | Implement Item 17 in PHP | Using approved UI design. See item number above. |  | 2019-07-15
35 | Test Functionality | Test all components according to spec. | All | 2019-07-15
36 | Fix Issues | Identify and fix and issues that arise. | All | 2019-07-15
37 | Practice Demo | Presenter and backup will prepare and practice demo. |  | 2019-07-15
38 | Present | Presenter and backup will present to TA. | JH | 7/15 11:30 PM EST

## Extra
CS 6400 Group Project |  |  | Revised: | 2019-07-15
Phase 3 Action Plan
Team 29
Members: Joseph Henn, Andrew Nagy, Ashkan Yousefi, Lei Fan
Item # | Action Item | Details | Member(s) | Est. Completion (EDT)
1 | Wireframing is added | Balsamiq is used for the wireframing | AY